Supply Chain Issues Review

Action Plan based on meeting agenda and Teams transcript

# Executive Context

Purpose: Stabilize the supply chain, reduce production disruption, and address compliance risks related to components BIND567, COMP042, and COMP043.

Primary risks discussed: BIND567 quality control failures and molecular inconsistencies; COMP042 logistics and traceability gaps; COMP043 GMP violations, erratic deliveries, and stockouts.

Governance approach: Use a cross-functional task force with weekly updates, clear owners, supplier escalation, audit discipline, and documented corrective actions.

# Critical Issues Discussed

| Component | Issue | Operational / compliance impact | Primary response |
| --- | --- | --- | --- |
| BIND567 | Inconsistent molecular composition and high rejection risk | Production delays, product stability concerns, and FDA compliance exposure | Validate current batches, tighten incoming controls, escalate EcoSupply, and onboard an alternative supplier |
| COMP042 | Supply chain delays, missing/incorrect lot documentation, and traceability gaps | Batch validation blockers, contamination concerns, and production bottlenecks | Audit PrimeLogistics, document traceability gaps, and prepare corrective-action evidence for FDA review |
| COMP043 | Supplier cleanroom protocol gaps, delivery misses, and stockouts | Contamination risk, reduced production continuity, and resource reallocation across product lines | Drive supplier remediation while exploring parallel sourcing |

# General Strategies

| Action | Owner | Scope | Expected outcome / rationale |
| --- | --- | --- | --- |
| Create a cross-functional task force | Sarah Nakamura / team leads | All components | Coordinate quality, procurement, production, and supplier remediation workstreams with weekly progress updates. |
| Prioritize FDA compliance readiness | Maria Sanchez with input from Quality and Production | BIND567, COMP042, COMP043 | Maintain clear documentation of deviations, traceability gaps, corrective actions, and supplier remediation evidence. |
| Use dual-track supplier management | Ravi Patel / Procurement | BIND567, COMP043 | Escalate current suppliers while preparing alternative or parallel sourcing to protect production continuity. |
| Focus on production continuity | Eleanor Wright / Production | COMP042, COMP043 | Identify bottlenecks, resource impacts, and batch interruptions early so mitigation actions can be prioritized. |

# Immediate Actions

| Action | Owner | Scope | Expected outcome / rationale |
| --- | --- | --- | --- |
| Validate current BIND567 batches | David Okoro / Quality | BIND567 | Confirm batch quality and contain molecular inconsistency risk before additional downstream production impact. |
| Tighten incoming material controls | David Okoro / Quality | BIND567 | Increase controls on inbound materials to reduce defect risk and stabilize manufacturing reactions. |
| Escalate with EcoSupply and request a concrete corrective-action timeline | Sarah Nakamura and David Okoro | BIND567 | EcoSupply acknowledged the issue but had not provided a concrete timeline. |
| Contact previously vetted secondary suppliers | Ravi Patel / Procurement | BIND567 | Expedite contingency onboarding for BIND567 supply continuity. |
| Launch immediate PrimeLogistics audit | Ravi Patel / Procurement | COMP042 | Review shipment delays, lot-number mismatches, manifest accuracy, and traceability controls. |
| Document traceability gaps and corrective actions for FDA review | Maria Sanchez | COMP042 | Prepare a comprehensive report covering discrepancies and planned remediation. |
| Coordinate supplier remediation plan for GMP gaps | Maria Sanchez | COMP043 | Establish remediation timeline and confirm required cleanroom protocol improvements. |
| Assign production liaison for documentation support | Eleanor Wright | COMP042 / COMP043 | Connect production evidence and operational impacts into the documentation workstream. |
| Allocate procurement resources for supplier onboarding and audits | Ravi Patel | BIND567 / COMP042 / COMP043 | Speed execution on contingency sourcing and supplier audit activity. |

# Short-Term Actions (1-3 weeks)

| Action | Owner | Scope | Expected outcome / rationale |
| --- | --- | --- | --- |
| Complete alternative supplier onboarding plan | Ravi Patel / Procurement | BIND567 | Convert previously vetted secondary supplier outreach into a readiness plan for rapid transition if needed. |
| Complete PrimeLogistics audit findings and corrective-action path | Ravi Patel / Procurement | COMP042 | Define required fixes for delayed shipments, mismatched lot numbers, malformed manifests, and traceability weaknesses. |
| Finalize and circulate traceability and compliance report | Maria Sanchez | COMP042 | Ensure discrepancies, corrective actions, and FDA-facing evidence are captured in one controlled summary. |
| Evaluate need for alternative sourcing for COMP042 | Procurement with Quality and Production input | COMP042 | Use audit results and production impact to decide whether alternate sourcing is required. |
| Confirm COMP043 supplier remediation timeline and governance checkpoints | Maria Sanchez / Quality / Procurement | COMP043 | Track cleanroom protocol remediation, delivery discipline, and stockout recovery. |
| Build parallel sourcing options for COMP043 | Ravi Patel / Procurement | COMP043 | Maintain continuity while supplier corrective actions are underway. |
| Conduct weekly progress review | Sarah Nakamura / task force | All components | Review action owners, blockers, compliance exposure, and supplier progress. |

# Ongoing Actions

| Action | Owner | Scope | Expected outcome / rationale |
| --- | --- | --- | --- |
| Maintain weekly task force cadence | Sarah Nakamura / cross-functional task force | All components | Keep actions visible, owners accountable, and risks escalated quickly. |
| Monitor quality, traceability, delivery, and GMP indicators | Quality, Procurement, and Production leads | All components | Use the discussed issue categories as standing indicators for risk tracking. |
| Preserve FDA-ready documentation | Maria Sanchez / Documentation owners | All components | Keep discrepancy logs, audit findings, supplier remediation evidence, and corrective actions updated. |
| Review supplier performance and contingency readiness | Ravi Patel / Procurement | All suppliers | Continue assessing whether current suppliers are improving or whether alternate sourcing should be activated. |
| Capture production impacts and mitigation needs | Eleanor Wright / Production | COMP042 / COMP043 | Track batch interruptions, resource reallocations, and downstream product-line impacts for leadership decisions. |

# Decision and Follow-Up Log

Meeting summary to include specific action owners and deadlines.

Team to reconvene in one week to review progress.

Task force to provide weekly updates on supplier, quality, production, and compliance actions.

Source: Teams Meeting Transcript.docx and meeting context for "test: Supply Chain Issues Review".